# SHARED EXPENSE PLATFORM — MASTER PRODUCT & ENGINEERING PLAN

Web-first, mobile-ready Splitwise-style expense sharing application

# 1. DOCUMENT PURPOSE

This document is the master implementation plan for a production-grade shared-expense platform. Each product module is treated as an Epic. Features inside an Epic are implementation Tasks; larger features are split into backend/domain and frontend/integration tasks where that produces a safer delivery unit.

Primary goals

• Make shared expenses, balances, and settlements trustworthy and easy to understand.

• Launch a responsive web application first without creating a dead-end for iOS/Android.

• Keep all financial calculations in a testable backend domain layer.

• Build an API and data model that can serve web, PWA, and native mobile clients.

• Deliver an MVP quickly, then add advanced Splitwise-class capabilities in controlled phases.

# 2. RECOMMENDED TECHNOLOGY STACK

Backend: Node.js + TypeScript + NestJS. NestJS is a strong fit because modules, dependency injection, guards, interceptors, validation, OpenAPI support, queues, and testing conventions scale well as the product grows.

Frontend: Vue 3 + TypeScript + Vite + Vue Router + Pinia + TanStack Query for Vue. Use a responsive component system and PWA support from the beginning.

Mobile strategy: build the web UI mobile-first. Package selected Vue screens using Capacitor for iOS/Android when native distribution is required. This gives maximum Vue reuse. If the future mobile UX becomes highly native or complex, the same NestJS API can serve a separate NativeScript/React Native/Flutter client without backend changes.

Database: PostgreSQL.

ORM: Prisma recommended for schema readability, migrations, generated TypeScript types, transactions, and developer speed. Drizzle is a valid alternative if lower-level SQL control is preferred.

Authentication: Google OAuth/OIDC initially. Keep an internal User and AuthIdentity model so Apple Sign-In or email login can be added later without redesigning the domain.

Caching/background work: Redis + BullMQ for recurring expenses, reminders, notification fan-out, report generation, and retryable jobs.

Object storage: S3-compatible object storage for receipts and attachments; use signed upload/download URLs.

Notifications: Firebase Cloud Messaging for web/Android; APNs through the mobile notification layer for iOS. Email provider can be added for invitations/reminders.

API: REST JSON, versioned under /api/v1, OpenAPI/Swagger generated by NestJS. REST is simpler than GraphQL for this domain and works well for mobile caching.

Validation: class-validator/class-transformer or Zod at API boundaries; database constraints for financial invariants.

Money: store monetary amounts in integer minor units plus ISO currency code; never use floating-point for ledger calculations.

Dates: UTC timestamps in storage; user timezone only for display and recurring-schedule interpretation.

Observability: structured logs, request/correlation IDs, Sentry or equivalent error monitoring, metrics, health/readiness endpoints.

DevOps: Docker, CI/CD, linting, unit/integration/E2E tests, automated migrations, separate local/dev/staging/production environments.

# 3. HIGH-LEVEL ARCHITECTURE

Clients (Vue Web/PWA, later Capacitor iOS/Android) → HTTPS → NestJS API → PostgreSQL. Redis/BullMQ handles asynchronous work. Object storage holds receipts. Notification/email adapters send outbound messages. External adapters isolate Google OAuth, exchange-rate providers, OCR, and future payment providers.

Recommended NestJS modules: Auth, Users, Friends, Groups, Expenses, Splits, Ledger, Settlements, Currencies, RecurringExpenses, Activities, Notifications, Reminders, Attachments, Comments, Reports, Search, Analytics, Admin, Jobs, Audit, Health.

Core principle: Expense records and Settlement records are immutable financial facts where possible. Editing creates controlled revisions/audit events. Balance views are derived from ledger entries; do not make a mutable “balance” field the source of truth.

# 4. CORE DATA MODEL

User: id, name, email, avatar, defaultCurrency, timezone, locale, status.

AuthIdentity: userId, provider, providerSubject.

Friendship: requesterId, addresseeId, status, timestamps.

Group: id, name, type, image, defaultCurrency, simplifyDebtsEnabled, status.

GroupMember: groupId, userId, role, joinedAt, leftAt.

Expense: id, groupId nullable, description, totalMinor, currency, expenseDate, createdBy, status, version.

ExpensePayer: expenseId, userId, paidMinor.

ExpenseParticipant/Split: expenseId, userId, owedMinor, splitType, splitInput.

LedgerEntry: sourceType, sourceId, debtorUserId, creditorUserId, amountMinor, currency.

Settlement: fromUserId, toUserId, amountMinor, currency, method, groupId nullable, note, date, status.

Category, Attachment, Comment, ActivityEvent, RecurringExpense, Notification, Reminder, ExchangeRate, AuditEvent.

Use UUID/ULID identifiers, foreign keys, unique constraints, indexes on user/group/date/status, soft deletion only where auditability requires it.

# 5. EPIC 0 — ENGINEERING FOUNDATION

Task 0.1 — Monorepo/project bootstrap — 1.5 days

Description: establish repository structure for apps/api, apps/web and shared packages. Configure TypeScript strict mode, linting, formatting, environment validation, commit hooks and consistent scripts.

Acceptance: clean install/build/test commands work; CI can build both apps; environment secrets are not committed.

Task 0.2 — NestJS platform foundation — 1.5 days

Description: configure global validation, exception mapping, API versioning, Swagger/OpenAPI, request IDs, structured logging, health/readiness endpoints and standard response/error conventions.

Acceptance: invalid requests return stable errors; OpenAPI is generated; every request is traceable by correlation ID.

Task 0.3 — PostgreSQL + Prisma foundation — 2 days

Description: create schema conventions, migrations, seed framework, transaction helper, indexes and local database setup. Define money/currency conventions.

Acceptance: fresh environment can migrate/seed automatically; rollback/recovery procedure documented; no float money columns.

Task 0.4 — CI/CD and environments — 2 days

Description: PR checks for lint/typecheck/test/build; staging deployment on merge; production release workflow; secret management; migration step; Docker images.

Acceptance: failed checks block release; staging is reproducible; production secrets never live in source.

Task 0.5 — Test architecture — 1.5 days

Description: Vitest/Jest unit tests, Nest integration tests with test DB, frontend component tests, Playwright E2E, factories/fixtures.

Acceptance: representative unit, API integration and browser E2E tests execute in CI.

EPIC 0 effort: 8.5 days.

# 6. EPIC 1 — AUTHENTICATION & ACCOUNT

Task 1.1 — Google OAuth backend — 2 days

Description: validate Google OIDC tokens, map provider identity to internal user, issue secure application session/token, support refresh/revocation and first-login user creation.

Edge cases: duplicate email/provider identities, revoked Google account, disabled internal account.

Acceptance: new and returning users authenticate safely; protected endpoints reject invalid/expired credentials.

Task 1.2 — Login/session frontend — 1.5 days

Description: Google login UI, callback handling, session bootstrap, route guards, logout and expired-session recovery.

Acceptance: refresh preserves valid session; unauthorized routes redirect correctly; logout invalidates session.

Task 1.3 — Profile/preferences — 1.5 days

Description: edit name/avatar where allowed, default currency, timezone, locale, notification preferences.

Acceptance: changes persist and are reflected across new expenses and UI formatting.

Task 1.4 — Account security/data lifecycle — 2 days

Description: active-session visibility, revoke all sessions, account export request and deletion/deactivation workflow with financial-history retention rules.

Acceptance: user can terminate sessions; deletion does not corrupt historical shared ledgers.

EPIC 1 effort: 7 days.

# 7. EPIC 2 — FRIENDS, CONTACTS & INVITATIONS

Task 2.1 — Friendship domain/API — 2 days

Description: request, accept, decline, remove, list and search friendships. Prevent self-friendship and duplicates.

Acceptance: state transitions are authorized and idempotent.

Task 2.2 — Friends UI — 1.5 days

Description: friend list, pending requests, search, add/remove actions and per-friend balance preview.

Acceptance: states update without full reload and display clear empty/error states.

Task 2.3 — Invite links/email — 2 days

Description: signed expiring invite token, landing flow and optional email delivery. Existing users should attach without duplicate accounts.

Acceptance: expired/reused tokens are safe; successful invite creates intended relationship.

Task 2.4 — Contact import/mobile contact picker — 1.5 days later-phase

Description: permission-aware contact selection on supported mobile clients; never upload the full address book unnecessarily.

Acceptance: explicit permission and minimal data processing.

EPIC 2 effort: 5.5 MVP + 1.5 later.

# 8. EPIC 3 — GROUPS & MEMBERSHIP

Task 3.1 — Group CRUD — 2 days

Description: create/edit/archive group, type, photo, default currency and debt-simplification preference.

Acceptance: authorized members can view; only permitted roles can modify.

Task 3.2 — Membership/roles — 2.5 days

Description: add/invite/remove members, leave group, owner/admin/member roles, safeguards when balances remain.

Acceptance: cannot silently remove financial history; permissions enforced server-side.

Task 3.3 — Group UI — 2 days

Description: group list/detail, member list, balances, recent expenses/activity and group settings.

Acceptance: responsive mobile-first UX and deep-linkable group routes.

Task 3.4 — Archive/delete semantics — 1 day

Description: archive completed groups; hard deletion only where legally/safely possible.

Acceptance: historical ledger remains consistent.

EPIC 3 effort: 7.5 days.

# 9. EPIC 4 — EXPENSE CREATION & MANAGEMENT

Task 4.1 — Expense domain/API — 3 days

Description: create expense for friend or group with description, amount, currency, date, category, notes, payers and participants. Execute payer/split/ledger writes transactionally.

Acceptance: expense cannot exist partially; payer totals equal expense total; owed totals equal expense total.

Task 4.2 — Add-expense UI — 3 days

Description: fast mobile-first form, group/friend selector, payer selection, participant selection, split preview, validation and confirmation.

Acceptance: common equal-split flow is achievable with minimal steps; invalid totals cannot submit.

Task 4.3 — Edit expense/revision — 2 days

Description: authorized edits recalculate ledger atomically and produce activity/audit history.

Acceptance: balances before/after edit reconcile exactly; stale concurrent edit is rejected or safely versioned.

Task 4.4 — Delete/restore expense — 1.5 days

Description: soft-delete or reversal semantics; recalculate derived ledger and retain audit evidence.

Acceptance: deleted expense disappears from active totals without destroying audit history.

Task 4.5 — Expense detail/history — 1.5 days

Description: detail screen showing who paid, who owes, category, attachments, comments and change history.

Acceptance: user can understand how the expense affected their balance.

EPIC 4 effort: 11 days.

# 10. EPIC 5 — SPLIT ENGINE

Task 5.1 — Equal split — 1 day

Description: deterministic minor-unit allocation including remainder cents/satang.

Acceptance: sum always equals total; deterministic remainder assignment tested.

Task 5.2 — Exact amount split — 1 day

Description: user enters each participant amount.

Acceptance: total must equal expense amount.

Task 5.3 — Percentage split — 1.5 days

Description: percentage inputs with precise rounding strategy.

Acceptance: percentages and generated monetary shares reconcile.

Task 5.4 — Shares/ratio split — 1.5 days

Description: allocate amount proportional to integer/decimal shares.

Acceptance: zero/invalid shares rejected; rounding tested.

Task 5.5 — Multiple payers — 2 days

Description: allow several members to fund one expense in different amounts while participants owe independently.

Acceptance: payer total and owed total each reconcile to expense total; ledger output is correct.

Task 5.6 — Split-engine property tests — 2 days

Description: randomized/property-based tests for totals, rounding, negative/zero inputs and participant combinations.

Acceptance: invariant suite proves no money is created or lost.

EPIC 5 effort: 9 days.

# 11. EPIC 6 — LEDGER, BALANCES & DEBT SIMPLIFICATION

Task 6.1 — Ledger generation — 3 days

Description: translate each expense/settlement into auditable obligations. Keep algorithm isolated from controllers/UI.

Acceptance: deterministic entries; every source can be traced; transaction rollback is complete.

Task 6.2 — Balance queries — 2.5 days

Description: overall, per-friend and per-group balances; “you owe”, “you are owed”, net position and detailed breakdown.

Acceptance: query totals reconcile to underlying ledger.

Task 6.3 — Balance UI — 2 days

Description: dashboard cards and detailed drill-down explaining the origin of balances.

Acceptance: user can trace a displayed amount to expenses/settlements.

Task 6.4 — Simplify debts algorithm — 2.5 days

Description: calculate each member’s net position and produce a reduced set of transfers while preserving net balances. Simplification is a presentation/settlement recommendation, not destructive rewriting of original expenses.

Acceptance: net position before/after simplification is identical; deterministic tests cover cycles and disconnected users.

EPIC 6 effort: 10 days.

# 12. EPIC 7 — SETTLE UP & PAYMENTS

Task 7.1 — Settlement API — 2 days

Description: record full/partial payment from one user to another, optional group, currency, method, date and note.

Acceptance: cannot settle unauthorized relationships; ledger updates transactionally.

Task 7.2 — Settle-up UI — 2 days

Description: suggested amount, partial amount, payer/payee direction, method/note and confirmation.

Acceptance: confirmation immediately updates balance views.

Task 7.3 — Settlement edit/reversal/history — 1.5 days

Description: safe correction via reversal/replacement, history and audit events.

Acceptance: historical balances remain explainable.

Task 7.4 — External payment deep links/integrations — 3–8 days later

Description: optional provider-specific payment initiation; never mark paid solely because a link was opened. Webhooks/reconciliation required for automatic confirmation.

EPIC 7 effort: 5.5 MVP + integration-specific later effort.

# 13. EPIC 8 — ACTIVITY, COMMENTS & AUDIT

Task 8.1 — Activity event model — 1.5 days

Description: normalized events for expense/group/member/settlement/comment changes.

Acceptance: actor, entity, timestamp and safe display payload recorded.

Task 8.2 — Activity feed UI/API — 1.5 days

Description: paginated personal/group activity feed with readable event text.

Acceptance: stable pagination; authorization prevents cross-group leakage.

Task 8.3 — Expense comments — 2 days

Description: add/edit/delete own comments; optional mentions later.

Acceptance: only expense participants/group members can access discussion.

Task 8.4 — Security audit log — 1.5 days

Description: separate operational audit trail for sensitive changes, admin actions and authentication events.

Acceptance: audit entries are append-oriented and restricted.

EPIC 8 effort: 6.5 days.

# 14. EPIC 9 — CATEGORIES, SEARCH & FILTERING

Task 9.1 — Categories — 1 day

Description: system categories plus optional user-defined categories and icons.

Acceptance: category deletion does not invalidate historical expenses.

Task 9.2 — Search API — 2 days

Description: search expense descriptions, groups and people; PostgreSQL indexes/full-text search initially.

Acceptance: scoped authorization and acceptable response time on target dataset.

Task 9.3 — Filters/sorting UI — 1.5 days

Description: date, category, person, group, currency, settled state and sort options with URL/query persistence.

Acceptance: filters combine predictably and can be cleared.

EPIC 9 effort: 4.5 days.

# 15. EPIC 10 — RECEIPTS & ATTACHMENTS

Task 10.1 — Secure attachment service — 2 days

Description: signed uploads, MIME/size validation, metadata, authorization, malware-scanning hook and lifecycle policy.

Acceptance: private files are not publicly enumerable; unauthorized download fails.

Task 10.2 — Receipt UI — 1.5 days

Description: upload/camera capture, preview, remove and view attachments.

Acceptance: mobile camera flow works after Capacitor packaging; web file upload works now.

Task 10.3 — OCR extraction — 3–5 days V2

Description: asynchronously extract merchant/date/total and present suggestions; never silently overwrite user-entered financial data.

Acceptance: extraction failure does not block expense creation; user confirms suggested values.

EPIC 10 effort: 3.5 MVP + 3–5 V2.

# 16. EPIC 11 — MULTI-CURRENCY

Task 11.1 — Currency model and formatting — 1.5 days

Description: ISO 4217 codes, minor-unit metadata and locale formatting.

Acceptance: currencies with 0/2/3 decimal minor units handled correctly.

Task 11.2 — Exchange-rate provider — 2 days

Description: adapter interface, cached rates, timestamp/source, fallback and manual rate support.

Acceptance: historical expense retains rate context; provider outage is handled gracefully.

Task 11.3 — Converted balance/reporting — 2.5 days

Description: show native obligations plus optional converted summaries; do not hide exchange-rate assumptions.

Acceptance: conversion math is deterministic and labeled.

EPIC 11 effort: 6 days.

# 17. EPIC 12 — RECURRING EXPENSES & BACKGROUND JOBS

Task 12.1 — Recurrence model — 2 days

Description: daily/weekly/monthly/yearly/custom schedules, timezone, next run, end date, pause/resume.

Acceptance: daylight-saving/timezone behavior defined; duplicate generation prevented.

Task 12.2 — BullMQ scheduler/worker — 2.5 days

Description: idempotent job creation, locking, retry/backoff, dead-letter visibility and monitoring.

Acceptance: retry cannot duplicate financial expense; failed jobs are observable.

Task 12.3 — Recurring-expense UI — 1.5 days

Description: create/edit/pause/resume and next-occurrence preview.

Acceptance: schedule preview matches backend calculation.

EPIC 12 effort: 6 days.

# 18. EPIC 13 — NOTIFICATIONS & REMINDERS

Task 13.1 — Notification preference/domain — 1.5 days

Description: event types, channels, read state, preferences and deduplication.

Acceptance: disabled preference prevents corresponding outbound notification.

Task 13.2 — In-app notification center — 1.5 days

Description: list/unread count/mark read/deep link.

Acceptance: links open correct authorized entity.

Task 13.3 — Push notifications — 2.5 days

Description: FCM token registration, device lifecycle, web push and later native push adapter.

Acceptance: invalid tokens are retired; sensitive details are minimized on lock screen.

Task 13.4 — Reminders — 2 days

Description: manual and scheduled payment reminders with abuse/rate limits.

Acceptance: users cannot spam another user; reminders are logged.

Task 13.5 — Email notifications/invitations — 1.5 days

Description: provider adapter, templates, unsubscribe/preference behavior where applicable.

EPIC 13 effort: 9 days.

# 19. EPIC 14 — DASHBOARD & ANALYTICS

Task 14.1 — Home dashboard — 2 days

Description: net balance, total owed/owing, recent activity, friends/groups and quick actions.

Acceptance: figures reconcile with balance API; responsive loading/error states.

Task 14.2 — Spending analytics API — 2 days

Description: totals by month/category/group/person with bounded date ranges.

Acceptance: only accessible data aggregated; queries indexed and tested.

Task 14.3 — Charts/insights UI — 2 days

Description: category distribution, monthly trend and group spending views.

Acceptance: accessible labels; no misleading converted-currency aggregation.

Task 14.4 — Budgeting — 3 days later

Description: optional personal/group/category budgets and threshold alerts.

EPIC 14 effort: 6 days core + 3 later.

# 20. EPIC 15 — REPORTS & EXPORTS

Task 15.1 — CSV export — 1.5 days

Description: export expenses/settlements for user/group/date range with stable columns.

Acceptance: exported totals reconcile; authorization enforced.

Task 15.2 — PDF/statement generation — 2.5 days

Description: asynchronous printable statement with balances, expenses and settlements.

Acceptance: large reports generated by worker, not request thread.

Task 15.3 — Account data export — 2 days

Description: portable archive of user-owned data and references to shared financial records.

Acceptance: privacy-safe and auditable export request.

EPIC 15 effort: 6 days.

# 21. EPIC 16 — WEB/PWA & MOBILE READINESS

Task 16.1 — Responsive design system — 2 days

Description: mobile-first navigation, forms, modals/sheets, typography, accessibility and reusable components.

Acceptance: key flows work at phone/tablet/desktop breakpoints.

Task 16.2 — PWA — 2 days

Description: manifest, installability, icons, service worker and safe caching strategy.

Acceptance: installable web app; authenticated financial API responses are not dangerously cached.

Task 16.3 — Offline/read resilience — 3 days V2

Description: cached read models and queued non-financial drafts. Avoid blindly queuing final money mutations offline because conflicts can corrupt expectations.

Acceptance: clear offline status; server reconciliation is explicit.

Task 16.4 — Capacitor iOS/Android packaging — 4–6 days V2

Description: native projects, deep links, Google/Apple auth adjustments, camera, push, secure storage and app lifecycle.

Acceptance: same API contract works on web and both mobile platforms.

Task 16.5 — Store release pipeline — 2–4 days V2

Description: signing, environment config, privacy metadata, beta distribution and release checklist.

EPIC 16 effort: 4 MVP + 9–13 V2.

# 22. EPIC 17 — SECURITY, PRIVACY & ABUSE PREVENTION

Task 17.1 — Authorization matrix — 2 days

Description: define every resource/action permission; implement NestJS guards/policies; object-level authorization is mandatory.

Acceptance: negative authorization tests cover cross-user/group access.

Task 17.2 — API security — 2 days

Description: rate limiting, secure headers, CORS, CSRF strategy based on session model, input limits, dependency scanning and secret handling.

Acceptance: security checklist and automated tests pass.

Task 17.3 — Privacy/data retention — 2 days

Description: retention rules, deletion/anonymization, audit retention, attachment lifecycle and privacy documentation.

Acceptance: account deletion and shared-record retention behavior is explicit.

Task 17.4 — Threat model/security review — 2 days

Description: review auth takeover, IDOR, invite abuse, receipt exposure, notification leakage, financial tampering, replay, webhook spoofing and admin abuse.

Acceptance: high-severity findings resolved before production.

EPIC 17 effort: 8 days.

# 23. EPIC 18 — ADMIN & OPERATIONS

Task 18.1 — Admin RBAC — 1.5 days

Description: isolated admin roles and server-side permissions.

Acceptance: ordinary users cannot access admin APIs/UI.

Task 18.2 — User/group support tools — 2 days

Description: search accounts/groups, inspect non-secret metadata, disable abusive accounts; avoid arbitrary financial edits.

Acceptance: every admin action audited.

Task 18.3 — Feature flags/config — 1.5 days

Description: safely roll out OCR, recurring expenses, mobile features and experiments.

Acceptance: flags can target environment/percentage/cohort as needed.

Task 18.4 — Operational dashboards/runbooks — 2 days

Description: queue health, API error rate, latency, DB capacity, storage and notification failures; backup/restore and incident runbooks.

Acceptance: alerts have owners/actions; restore is tested.

EPIC 18 effort: 7 days.

# 24. EPIC 19 — ADVANCED/AI FEATURES

Task 19.1 — Natural-language expense creation — 4–6 days

Description: parse text such as “Dinner 1800 THB, I paid, split equally with A and B” into a draft only. Resolve people/groups and require confirmation before financial mutation.

Acceptance: ambiguous input asks for correction; no AI output directly writes a ledger without deterministic validation.

Task 19.2 — Smart categorization — 2–4 days

Description: suggest category from merchant/description/history with user confirmation.

Task 19.3 — Duplicate detection — 2–3 days

Description: score potential duplicates using amount/date/merchant/group/participants and warn before submission.

Task 19.4 — Spending insights — 3–5 days

Description: generate explainable insights from deterministic aggregates; avoid presenting generated text as financial advice.

EPIC 19 effort: 11–18 days later.

# 25. CROSS-CUTTING API REQUIREMENTS

Use resource-oriented endpoints, e.g. /auth, /users/me, /friends, /groups, /groups/:id/members, /expenses, /expenses/:id, /settlements, /balances, /activities, /recurring-expenses, /notifications, /reports. Support cursor pagination for feeds. Use idempotency keys for financial creates where retries are plausible. Use optimistic versioning for expense edits. Standardize error codes such as VALIDATION_ERROR, FORBIDDEN, SPLIT_TOTAL_MISMATCH, STALE_VERSION and IDEMPOTENCY_CONFLICT.

# 26. FINANCIAL DOMAIN INVARIANTS — RELEASE BLOCKERS

• Expense total must be positive and represented in integer minor units.

• Sum of payer contributions equals expense total.

• Sum of participant obligations equals expense total.

• Ledger generation is deterministic.

• Every ledger entry has an auditable source.

• Editing/deleting an expense cannot leave orphan obligations.

• Settlement direction and amount are explicit.

• Simplified debts preserve every member’s net position.

• Job retries cannot duplicate recurring expenses or settlements.

• Multi-currency totals are never mixed without an explicit exchange rate and valuation timestamp.

# 27. TEST STRATEGY

Unit: split algorithms, ledger, debt simplification, currency rounding, recurrence and authorization policies.

Property-based: random totals/participants to prove payer and owed invariants.

Integration: API + real PostgreSQL test container for transactions, constraints and authorization.

Contract: OpenAPI validation for web/mobile clients.

Frontend: components/forms plus critical state transitions.

E2E: login; create group; add expense; each split type; edit/delete; settle partially/fully; verify balances; invitation; receipt; recurring expense; notification.

Performance: balance/feed/search endpoints on realistic seeded datasets.

Security: IDOR/object authorization, token/session abuse, upload validation, rate limits and dependency scanning.

# 28. DELIVERY PHASES

Phase 0 — Foundation (Week 1–2): Epic 0 plus architecture/schema skeleton.

Phase 1 — MVP Core (Week 3–8): Auth, friends, groups, expense CRUD, equal/exact/percentage/shares, multiple payers, ledger/balances, settle-up, activity, categories/search, responsive dashboard and baseline security.

Phase 2 — Production V1 (Week 9–12): receipts, notifications, reminders, multi-currency, exports, PWA, observability/admin, hardening and E2E/performance/security review.

Phase 3 — V2 (Week 13–17): recurring expenses, OCR, richer analytics, offline resilience, Capacitor iOS/Android, native push/camera/deep links, store beta pipeline.

Phase 4 — Advanced (after V2): AI entry/categorization, duplicate detection, budgets, payment integrations and richer insights.

# 29. EFFORT SUMMARY

Core MVP engineering estimate: approximately 60–75 developer-days depending on UI polish and how much notification/reporting scope is included.

Production V1: approximately 85–105 developer-days cumulative.

V2 including recurring/OCR/mobile packaging: approximately 110–135 developer-days cumulative.

Advanced backlog: add approximately 15–30+ developer-days, excluding provider-specific payment integrations.

Solo experienced full-stack developer, full-time: MVP 10–14 calendar weeks; production V1 4–5 months; V2/mobile-ready product 5–7 months. With strong AI coding assistance, boilerplate speed improves, but ledger correctness, security, E2E testing, mobile store work and production hardening still require human review; plan a 15–20% buffer.

Solo evenings/weekends (~15–20 h/week): MVP roughly 5–7 months; V1 7–10 months.

Small team (2 engineers): MVP roughly 6–8 weeks; V1 10–14 weeks; V2 14–18 weeks, assuming parallel backend/frontend work and shared QA ownership.

Small team (3 engineers including strong frontend/mobile ownership): MVP roughly 5–7 weeks; V1 8–12 weeks; V2 12–16 weeks.

These are engineering estimates, not promises; app-store review, design changes and external provider approvals can add calendar time.

# 30. MVP DEFINITION OF DONE

MVP is complete when a user can sign in with Google, manage friends, create/manage groups, create/edit/delete expenses, choose multiple payers, split equally/exactly/by percentage/by shares, view trustworthy balances, settle fully/partially, view activity/history, search/filter expenses, use the product comfortably on mobile web and desktop, and the system has authorization, auditability, automated tests, CI/CD, monitoring and backups appropriate for an initial production release.

# 31. PRODUCT/UX REQUIREMENTS

Prioritize “Add expense” and “Settle up” as primary actions. Always preview split results before commit. Every balance must be explainable. Destructive financial changes require confirmation. Use skeleton/loading, empty, error and offline states consistently. Meet WCAG-oriented keyboard/focus/contrast expectations. Support deep links to group/expense/notification targets. Do not expose internal IDs or technical errors to users.

# 32. NON-FUNCTIONAL REQUIREMENTS

Availability target for early production: 99.9% where practical. Define SLOs for API latency and error rate after traffic baseline exists. Backups: automated PostgreSQL backups with point-in-time recovery if hosting supports it; periodically test restore. Security: TLS everywhere; encrypted managed storage; least privilege. Performance: paginate all unbounded lists; avoid N+1 queries; cache only safe derived/read data. Scalability: stateless API replicas; workers scale independently. Accessibility and localization are first-class UI concerns.

# 33. RISKS & MITIGATIONS

Financial rounding/ledger defects — mitigate with integer minor units, domain invariants, property tests and reconciliation tests.

Scope explosion — lock MVP and keep OCR/AI/payment integrations out until core ledger is stable.

Web-to-mobile rewrite — mitigate with responsive Vue, shared TypeScript packages, Capacitor-compatible patterns and API-first architecture.

Offline conflicts — permit safe cached reads/drafts first; avoid automatic offline financial commits until conflict strategy is proven.

Multi-currency confusion — preserve native currency and rate provenance; label converted summaries.

Notification spam — preference controls, deduplication and rate limits.

Receipt privacy — private object storage and short-lived signed URLs.

External provider lock-in — adapters/interfaces for auth, rates, storage, email/OCR/payment providers.

# 34. IMPLEMENTATION ORDER / CRITICAL PATH

Foundation → Auth → Users/Friends → Groups → Expense + Split Engine → Ledger → Balances → Settle Up → Activity → Dashboard → Search/Categories → Security hardening → Receipts/Notifications → Multi-currency → Reports/PWA → Recurring jobs → Mobile packaging → Advanced features.

Do not start AI or payment integrations before the deterministic financial core has strong automated coverage.

# 35. REVIEW PASS — PRODUCT, ARCHITECTURE, BACKEND, FRONTEND/MOBILE, QA & SECURITY

A second-pass completeness review was applied from six perspectives.

Product review: confirmed the complete lifecycle from onboarding through group expense, balance explanation and settlement; added archive semantics, invitations, data export, budgets/advanced backlog and clear MVP boundary.

Architecture review: added API-first boundaries, adapter pattern, Redis/BullMQ, object storage, idempotency, optimistic versioning, observability and independent workers.

Backend review: added integer money, transactional payer/split/ledger writes, immutable/auditable financial facts, indexes, background-job idempotency and exchange-rate provenance.

Frontend/mobile review: selected Vue 3 mobile-first + PWA + Capacitor as the highest-reuse route; added deep links, secure native capabilities, offline safety and store-release work.

QA review: added property-based financial tests, real-Postgres integration tests, E2E critical journeys, performance tests and explicit release-blocking invariants.

Security review: added object-level authorization, rate limiting, session revocation, private receipt access, audit logs, threat modeling, admin separation, privacy retention and anti-spam controls.

Important limitation: this review is a multi-perspective verification pass within the available environment; it is not a set of independently running external agents. The plan deliberately incorporates the checks those specialist reviews should perform.

# 36. RECOMMENDED FIRST SPRINT

1) Bootstrap monorepo and CI.

2) NestJS API foundation + PostgreSQL/Prisma migrations.

3) Vue 3 shell with mobile-first navigation.

4) Google OAuth end-to-end.

5) User/profile model.

6) Group + membership schema/API.

7) Define Expense/Payer/Split/Ledger schemas before building the expense UI.

8) Implement equal-split engine with exhaustive tests.

9) Add first end-to-end journey: login → group → equal expense → balance.

10) Review the domain model before expanding split types.

# 37. FINAL RECOMMENDATION

Proceed with Node.js + TypeScript + NestJS + PostgreSQL + Prisma for the backend and Vue 3 + TypeScript + Vite for the frontend. Build responsive/mobile-first and enable PWA capabilities early. Use Capacitor for the first iOS/Android packaging because it maximizes reuse of the Vue codebase. Keep the NestJS API client-agnostic so a fully native mobile UI can replace the Capacitor shell later without touching the financial domain. The highest engineering priority is not visual parity with Splitwise; it is a mathematically correct, auditable ledger and a frictionless expense-entry/settlement experience.